## Project schedule
| Europa project | [5 empty] | Project start: | [7 empty] | 2025-01-01
| VanArsdel, Ltd. | Project lead |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-12-30 to 2025-03-23
 | time axis 2024-12-30 to 2025-03-23
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Senior Developer (Tech Lead)
| Arhitectura sistemului și setup infrastructură |  | 0% | 2025-01-01 | 2025-01-15 | 15
| sistem de autentificare și autorizare | Hayden Cook | 0% | 2025-01-16 | 2025-01-30 | 15
| Integrare API-uri externe (bănci, curs valutar) | Jens Martensson | 0% | 2025-01-31 | 2025-02-14 | 15
| Configurare pipeline CI/CD | Nuria Acevedo | 0% | 2025-02-15 | 2025-02-22 | 8
| Code review și mentoring (Ongoing) | Nuria Acevedo | 0% | 2025-02-23 | 2025-03-30 | 36
Developer #1 (Backend Focus)
| Crearea modelelor de date și scheme DB |  | 0% | 2025-01-01 | 2025-01-08 | 8
| Implementare servicii tranzacții (CRUD) | Hayden Cook | 0% | 2025-01-09 | 2025-01-30 | 22
| Logica de import extrase bancare | Jens Martensson | 0% | 2025-01-31 | 2025-02-14 | 15
| Generare rapoarte (PDF/Excel) | Nuria Acevedo | 0% | 2025-02-15 | 2025-03-01 | 15
| Optimizare performanță backend | Olivia Wilson | 0% | 2025-03-02 | 2025-03-09 | 8
| Optimizare performanță backend | Olivia Wilson | 0% | 2025-03-10 | 2025-03-17 | 8
Developer #2 (Frontend Focus)
| Implementare UI dashboard principal |  | 0% | 2025-01-08 | 2025-01-22 | 15
| Pagina de gestionare tranzacții | Hayden Cook | 0% | 2025-01-23 | 2025-02-06 | 15
| Formulare bugete și alerte | Jens Martensson | 0% | 2025-02-07 | 2025-02-21 | 15
| Vizualizări grafice (charts) | Nuria Acevedo | 0% | 2025-02-22 | 2025-03-08 | 15
| Responsive design și teste cross-platform | Olivia Wilson | 0% | 2025-03-09 | 2025-03-16 | 8
Junior Developer
| Implementare componente UI simple |  | 0% | 2025-01-08 | 2025-02-05 | 29
| Teste unitare | Hayden Cook | 0% | 2025-01-15 | 2025-03-12 | 57
| Suport la documentație tehnică | Jens Martensson | 0% | 2025-02-05 | 2025-02-26 | 22
| Monitorizare bug-uri post-lansare | Nuria Acevedo | 0% | 2025-03-12 | 2025-04-02 | 22
Marketing Specialist
| Research piață și competiție |  | 0% | 2025-01-01 | 2025-01-15 | 15
| Creare conținut promoțional | Hayden Cook | 0% | 2025-01-16 | 2025-02-06 | 22
| Campanie pre-lansare | Jens Martensson | 0% | 2025-02-07 | 2025-02-21 | 15
| Management rețele sociale | Nuria Acevedo | 0% | 2025-02-22 | 2025-03-24 | 31
| Analiză metrici utilizare | Olivia Wilson | 0% | 2025-03-12 | 2025-04-11 | 31
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.